## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Customer Family Violence Policy | Policy | This policy ensures Lower Murray Water (LMW) customer-facing employees respectfully and equitably support our customers who may be experiencing family violence and/or who require financial assistance. | For Review | No action taken | The review did not identify any additional required actions. Domestic and Family Violence awareness education and training for all LMW staff was held again in August 2023, and was a mandatory activity for all customer facing employees. Challenging of pre-conceived stereotyping was included in the education package. This policy was externally reviewed by the Essential Services Commission (ESC) after a reported breach within the water sector (not LMW). | Yes | Equity, Diversity and Inclusion (EDI) Officer and Senior Manager Customers Operations conducted research and consulted with relevant staff to ensure the GIA considered intersectionality (particularly disability, rural location, language barrier and First Nations status). In doing so, it was determined that customers experiencing family violence would not be further disadvantaged by intersectionality. LMWs website has been checked using a web accessibility evaluation tool known as WAVE®. This evaluation tool helps authors make their web content more accessible to individuals with disabilities. WAVE can identify many accessibility and Web Content Accessibility Guideline (WCAG) errors. Flagged concern reports of less than 5 are considered good; our website has No flagged concerns indicating a very high level of end-user experience for those with disability and/or using adaptive technologies.
Hardship Policy | Policy | This policy assists customers who may experience financial hardship and may need additional assistance and flexibility in paying. LMW's associated Hardship Program identifies and assists vulnerable customers to manage their water costs and usage. The policy applies to all LMW staff in their role of assisting customers who have difficulty in paying their account by enrolling the customers in the LMW Hardship Program. Note: LMW Hardship Policy and the Hardship Program were replaced late in the reporting period, replaced by the Customer Support Policy (see below for additional GIA undertaken on it). | For Review | Yes | As a result of the review, LMW consulted with local community and external organisations to ensure LMW Hardship program met the needs and supported all people, including women. All staff, and in particular customer-facing staff, are trained to identify indicators of family violence, and this training is on-going. The Customer Service Teams undergo specific training on family violence and hardship to ensure appropriate assistance is provided to customers. | Yes | Consultation with local community and external organisations was undertaken to ensure LMW Hardship program met the needs of all people and we recognise that each customer has a distinct set of circumstances and may respond differently to a multitude of stresses that are caused by, or result in, hardship. To ensure the intersectional lens applied is reflective of our current community representation, the policy is reviewed on an ongoing basis in consultation with our key partners to ensure the program/policy adequately meets our staff and customer needs.
Recruitment and Selection Procedure | Policy | LMW’s Recruitment and Selection Procedure is one of the Corporation’s strategies to demonstrate commitment to developing a diverse and inclusive workforce and to apply the principles of equity, fairness and transparency to all recruitment, selection and appointment processes. This procedure ensures that a standard approach is adopted for the recruitment of all vacant positions within LMW. | For Review | Yes | The review identified the following opportunities for improvement, which have been implemented: • LMW Conflict of Interest form to be updated in line with the Victorian Public Sector Commission (VPSC). • Review language and graphics for job advertisements to ensure gender equality and inclusivity. • Review the manner in which our job ads are written, including the method we stipulate individuals are to apply. • Review recruitment policy, advertising templates and Request to Fill form to ensure adjustments are made • References to 'reasonable adjustments' need to be included (initially it was updated to ' for people that may require additional adjustment' and we have subsequently further amended so individual do not feel they need to justify their requests). • Change the way pre-employment medical checks are administered for a particular individual, or the assessment itself, so as to remove unnecessary barriers so that all applicants can perform on an equitable basis. Current examples of reasonable adjustments LMW consider include: • conducting assessments in a wheelchair-accessible room • allowing applicants to take a rest break during an interview • providing written materials in an alternative format • allowing applicants to be accompanied by a support person. • providing the interview questions to the applicant prior to the interview The review confirmed LMW's commitment to gender balanced interview panels continues to occur, as is limiting the panel membership to three to ensure interview experience is as comfortable as possible. | Yes | LMW's Manager of People and Communications and HR Generalist conducted research to ensure the GIA considered Intersectionality. It was identified that community members may benefit from reasonable adjustments during the recruitment process, for example someone with disability, someone with limited English, those with caring commitments, and it prompted the further loosening of the 'reasonable adjustments' to anyone who feels they would benefit (i.e. no justification required).
Gifts, Benefits and Hospitality Policy | Policy | This policy aims to detail LMW's position on responding to offers of gifts, benefits and hospitality and the provision of such gifts, benefits and hospitality where relevant. This policy supports individuals and LMW to avoid conflicts of interest and maintain high levels of integrity and public trust. | For Review | Yes | Upon review of the Gifts, Benefits and Hospitality Policy two opportunities for improvement were identified • gender equity when gift purchasing • religious dietary requirements These two factors were implemented into the Policy and final draft sent to the Governance, People and Culture committee for review. | Yes | Board Administration Officer conducted research and conducted consultation with Diversity and Inclusion Officer to ensure the GIA considered intersectionality. It was identified that staff appointed to buy gifts should speak to the General Manager or the staff member being recognised for guidance to determine the choice of gift and to ensure all genders are equally considered. i.e. not simply default to candles for women and fishing gear for men. Board Administration Officer and Diversity and Inclusion Officer also ensured the policy was adjusted to ensure that staff consider not only allergy requirements but also religious dietary requirements when ordering catering.
Strategic and Customer Service Advisory Committee - Terms of Reference and Operating Rules | Policy | These operating rules apply to appointed members of the Strategic Advisory Committee (SAC) and the Rural Customer Service Advisory Committee(s) (CSAC). | For Review | Yes | Some wording was identified in the documents during the review that could impact people of different genders differently. References to 'his or her' were removed to ensure we are using gender neutral language. The documents were also amended to include reference to the Gender Equality Act. | Yes | The review did not identify any further areas of inequity. In accordance with LMW obligation under the Gender Equality Act, the LMW board will give consideration to matters including Diversity when recommending appointments to these committees.
Customer’s Chosen Support Representative Process Standard Operating Procedure (SOP) | Policy | The SOP works hand in hand to support the LMW's Customer Support Policy (see below for separate GIA conducted on it). It is a process to capture the customer's chosen representative or support person or authorised party to act and communicate on behalf of the customer experiencing financial hardship. This SOP ensures LMW applies compliant practices and proactive protection to ensure the health and safety of our customers in the Hardship Program (noting the Hardship Program has subsequently been replaced by the Customer Support Policy during the review period). | New | Yes | The GIA review of the SOP gave rise to the need to indicate the existence of the assistance in the LMW Customer Support Policy. The SOP is now published on LMW website and LMW internal intranet. We have developed a process for staff to refer to when recording into the customer record database and information on how to manage this request when notified by the customer or support person. We have interlinked this process to the LMW Manage Payment Assistance - Utility Relief Grant Scheme (URGS) process. | Yes | Intersectionality was considered during the GIA as per the Hardship Policy and Program (described earlier)
Manage Payment Assistance Utility Relief Grant Scheme (URGS) - Standard Operating Procedure (SOP) | Policy | This SOP supports customers who are seeking financial relief. Customers who are experiencing financial vulnerability may be eligible for government assistance such as the Utilities Relief Grant (URGS), if they hold an account is for residential purposes. An LMW staff member will assist by lodging an application for URGS on behalf of the customer. If the customer wishes to self-lodge their application or LMW is unable to complete the customers behalf, LMW will provide information and assistance to customers for lodging their applications. | New | Yes | During the GIA review process, it was identified that training should be provided to customer facing staff in how to recognise and help customers in need of support. This training was undertaken in 2023 and is now part of ongoing staff training and new staff inductions. We have also published information on LMW Website regarding Utilities Relief Grant (URGS) assistance. | Yes | In development of this SOP, it was considered that language barriers could pose further disadvantage, however our Customer Support policy has measures in place to reduce the effect of such barriers including the advertising and recommendation by staff of the Interpreter Services. This service also assists customer with speech and hearing impairment.
Social Media Policy | Policy | This policy provides guidance to LMW employees when using social media. All employees are responsible for understanding their responsibilities when using social media in their personal capacity with regards to employment with LMW. | For Review | No action taken | No action taken as a result of the review. The policy includes statements such as: • employees must ensure personal posted content does not compromise their capacity to perform their public sector role in an unbiased manner. • by respecting LMW values we ensure there will be no harm to people of different genders. | Yes | Intersectionality was considered while conducting the GIA and confirmed the policy contains :"It’s important to understand that non-compliance with this policy may constitute a breach of contract of employment or other contractual obligations, sexual harassment, discrimination, or some other contravention of the law or bring LMW or yourself into disrepute". Acknowledging the requirement for positive duty, we also combine the policy with staff education in diversity (modules including First Nations, Understanding Mental Health and Disability Awareness training), continual messaging and role modelling from Executive and Senior Leadership teams, and monitoring.
External Communications Policy | Policy | The purpose of this policy is to provide consistency in LMW’s approach to external communications, and list approved LMW spokespeople for media interviews/ statements. | For Review | No action taken | No action was taken as a result of the review. Due to this policy approach the authorised people that engage with of the media on behalf of LMW are Management and Board and they are routinely reviewing and working with both LMW's Code of Conduct and the Gender Equality Act. The list of approved spokespeople includes a cross section of genders. | Yes | LMW's Board and Senior Managers representing the organisation in the media are a cross section of genders, sexual orientation, ethnicities, abilities (acknowledging the disabilities of those identifying as such are not necessarily readily visually identifiable) and caring responsibilities.
Sponsorships and Donations Policy | Policy | LMW provides sponsorship for community groups, non-commercial educational facilities and not-for profit organisations in our local service region to deliver beneficial projects, events and programs that support the organisation’s vision for “a healthy and sustainable water future underpinned by LMW’s culture of performance excellence, built in partnership with our staff, customers and communities”. This policy provides a framework for consistency and transparency in the sponsorship process. | For Review | No action taken | No actions were required as a result of the review. The policy supports initiatives that directly relate to our industry and help educate our communities about water, sustainability and environmental conservation. LMW sponsored 20 socially and gender inclusive events during the reporting period. There was several sporting clubs including the Merbein Cobras basketball club, Three Colours FC, Red Cliffs Football Club, Nichols Point FC Soccer Club and Mildura Football Netball club who received sponsorship. Sponsorship was provided to these clubs for their work in social inclusion and diversity in membership. Many of the clubs that we sponsor prioritise cultural and gender inclusion. | Yes | In consultation with LMW's Engagement Officer and EDI Officer intersectional lenses were applied in assessment of the Sponsorship Criteria. An event/project must be held within LMW service region or be aimed at people who reside in our service region. Events must meet at least one of the criteria in each of the following categories: 1. Water Related Criteria • promote and encourage the responsible use of water and its conservation • educate the communities in our service area about water, sustainability, and environmental conservation 2. Social and Sustainability Criteria • demonstrate sustainable practices • provide a social benefit to our service region and communities • be socially inclusive. • be gender inclusive 3. Events/projects must provide a distinct benefit to at least one of our target markets • residential customers • irrigators and growers • early years and school children • local businesses • aboriginal and Torres Strait Islander community • culturally and Linguistically Diverse community Additionally, during the reporting period LMW donated water bottles to an organisation called Connected Beginnings. These water bottles were given to Aboriginal students starting their school journey. In celebration of Mallee District Aboriginal Services NAIDOC event at Mildura Primary School LMW sponsored 100 water bottles were donated to the students
Customer Support Policy | Policy | This policy applies to all LMW staff in their role of assisting customers who have difficulty in paying their account by enrolling the customers in the LMW Customer Support Program. | For Review | Yes | Upon review of the LMW Customer Support Policy, areas of improvement were identified (and subsequently actioned): • Hardship Program renamed to LMW Customer Support Program. • Interpreter Services added to assist customers with language barriers, speech and hearing impairment • Updated policy to simple language | Yes | Apply the intersectional lens during the review identified an opportunity for improvement in ensuring simple language was used. This break downs the barriers making it easier for readers to comprehend content. Subsequent assessment in regards to intersectionality (disability, rural location, language barrier and First Nations status)determined that customers experiencing financial hardship and needing additional assistance would not be further disadvantaged by intersectionality.
Customer Complaint Procedure | Policy | The purpose of this procedure is to define what a complaint is and how staff are to keep a record of documents and discussions of the complaint investigation and response. A complaint is recorded by creating a request in the Customer Record Management (CRM) software. This will trigger a workflow for the complaint investigation. When creating the request ensure that the Request Type is recorded correctly. The monthly complaint reporting to the Emergency Services Commission (ESC) arises from these. | For Review | No action taken | As this procedure does not detail the manner in which staff conduct the collection of complaint details from the customer (it's purely administrative), there were no applicable actions required as a result of the GIA. Notwithstanding the procedure being administrative in nature, all customer-facing staff have received Situational Awareness, Occupational Violence and Aggression training. Below noted are some topics that educate and support our customer - facing staff: • How to be safe in unsafe situations • Why do we need to be situationally aware? • Understanding levels of awareness • Assessing a situation • Recognising violence indicators • De-Escalation Skills • How to utilize action vs. reaction • Using cover and concealment With ongoing staff learning and development LMW Revenue/Debt collection staff completed additional training with E-Matrix (online learning platform). The training covered multiple topics regarding Customer Engagement and Collections & Hardship. | Yes | LMW Customer Feedback form was reviewed as part of the GIA to ensure customers have multiple ways to lodge feedback/issues. Feedback/Issues can be lodged by a customer or representative: • by online request via our website, • email or mail • request in writing • phone our call centre • visit one of our three offices located in Mildura, Swan Hill and Kerang
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated women's and all-gender secured changerooms and facilities for all women's and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are perceived as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and practices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Review language in position descriptions to ensure they are gender neutral and culturally safe (Pillar 1 - Employment Practices - Attract greater diversity in candidates through recruitment processes across all work groups) | Ongoing | This strategy was initiated in 2022, continued throughout 2023 as positions have become vacant, and as part of the PD classification/reclassification process. The language has been reviewed in current position descriptions (PDs) to ensure they are gender neutral and compatible with cultural safety; this will continue as PDs are created and endorsed. LMW has a double-check system in place whereby line managers develop draft PDs giving consideration to equality, diversity and inclusion (EDI) requirements, and then the People Team review and return to Manager should there be any outstanding issues identified. Our General Managers and Managing Director must endorse all finalised PDs, essentially providing a third gate-keeper check. Review of each existing PD occurs when a new recruitment process commences by the HR Generalist, Recruitment Coordinator and Hiring Manager. Reviewed PDs follow the same endorsement process as described above for new PDs. | All current PD's are gender neutral and culturally safe. We continue to challenge ourselves to determine whether each historical requirement is truly necessary and supportive of diversity. In 2024 all completed PDs from previous years will be reviewed and updated consistent with new process. The reviews undertaken to-date have not identified any trends of concern, and the preliminary application by line managers to request a new employee has only highlighted two instances (which were immediately rectified and explanatory communications between the People Team and relevant line manager occurred) where there was mention of 'tradesman' and 'young person' when referring to apprenticeship opportunities. | 2022 2023 2024 2025 | Hiring Managers HR Generalist | X |  | X |  | X |  | X
Review language and graphics for job advertisements and social media content to ensure gender neutral job advertisements (Pillar 1 - Employment Practices - Attract greater diversity in candidates through recruitment processes across all work groups) | Ongoing | This action was implemented from September 2021. The review of language and graphics for our job ads are an ongoing process. Vacant position advertising is drafted by the Hiring (usually line) Manager, who are provided the following tips to ensure we are creating an inclusive job advertisement: · Ensure key position terms are not gender specific · Use clear and concise language, be aware of tone · Get a team member to review to pick up language, tone or structure that is biased or exclusive · Be clear about LMW's goals around diversity and outline this in the ad The Hiring Manager then has the ad reviewed and approved by their General Manager, and then it is sent to the People Team who do a final check to ensure LMW's commitment to equality, diversity and inclusion (EDI) is maintained. We have removed the drivers licence requirement from our standard job ad templates, and make an assessment within each PD as to whether a drivers licence is critical to the role being performed. We recognise that the requirement may have disadvantaged women and people with disability, in particular, from applying for a position in the past. As at time of report, our job ad template (used internally and externally) contains the following highlighted statement: If you require any help with your application, accessibility or reasonable adjustments during the recruitment process please don’t hesitate to contact our Diversity & Inclusion Officer – Steph on (phone no) We are utilising photo's of real staff in our social media job adverts to demonstrate the diversity of our organisation and as we further increase our diversity, this will become a stronger message. | Increased social media interaction has been detected across the reporting periods on LinkedIn, Facebook and Seek (monitored by LMW Engagement Officer). The People Team, in conjunction with the Engagement Officer, monitor any repeat use of the same female staff in ads so as to avoid appearing tokenistic. LMW Facebook page is followed by 5.2k followers. Find below analytics we monitor and track from LMW Facebook page regarding community interaction of job advertisements: Post interactions with title only 936 reach - 22 engagements 1.8k reach - 57 post engagements 1.8k reach - 78 post engagements 2.0k reach - 57 post engagements Post interaction including staff photo's 2.2k reach - 69 post engagements 3.2k reach - 74 post engagements 3.5k reach - 148 post engagements 4.6k reach - 201 post engagements | 2022 2023 2024 2025 | Hiring Managers, People and Communications Teams | X |  | X |  | X |  | X
Celebrate roles and people that support breaking gender stereotypes, gender roles or prejudices by profiling them on social media and through internal communications (Pillar 1 - Employment Practices - Attract greater diversity in candidates through recruitment processes across all work groups) | Ongoing | LMW engage with Vic Water yearly to publish staff profiles to promote the diversity of careers available at LMW and the diversity of our workforce (different cultures, genders, abilities and ages). A selection of LMW published staff profiles within the Victorian Water Industry - Equity, Diversity & Inclusion Annual Performance Report are shown below: Case Study - Women in Trade Female employee was hired as a First Year Electrical Apprentice in March 2020. Female employee showed initiative and passion for the job before commencing with the business. Female employee reached out to the business to enquire about potential employment opportunities with LMW. Female employee brings LMW different opinions and a new dynamic to the team and encourages more women to add trades into their possible career options. Case Study - Embracing cultural heritage through a diverse workforce. Female employee joined LMW on 1 December 2021 as a Treatment Plant Operator. Female employee helps break down the gender stereotypes associated with operations based positions. Female employee pride and love for her work helps create a positive atmosphere and serves as a great example for young women who may be discouraged from entering the water treatment field. This supports LMW’s aim of increasing the number of women working within non-gender typical roles as highlighted in their Gender Equity Action Plan (GEAP). International Women in Engineering Day - LMW Facebook Post Female employee 1 completed her studies in Pharmaceutical Engineering and has been working in various roles across the food and beverage industry before joining us at LMW 18 months ago. Female employee is currently working on installing UV disinfection systems at our Mildura West and Seventh Street Water Treatment Plants. Female employee 2 is a Civil Engineer and joined LMW 18 months ago, first working on the design, surveying and project management of urban water and irrigation projects. More recently, has joined our Sunraysia Water Efficiency Project (SWEP) as a Surveillance and Operations Officer. Female employee expertise are highly valued and she is a critical member of the SWEP team, which is working to modernise and remove outdated water infrastructure across local irrigation districts. LMW will continue to promote the diversity of careers available at LMW on our social platforms, this helps us to attract greater diversity in candidates through the recruitment processes across all work groups | LMW have also conducted a public campaign through the local Mildura Living magazine highlighting the careers of specific people including our General Manager People and Stakeholders (Deb Fankhauser - she/her), and our People & Safety Officer (Belinda Ryan - she/her) outlining how LMW can provide rewarding career opportunities. The LMW Communications Team upload on LMW Facebook page events such as International Women's Day, Pride Month and Women in Engineering Day, Harmony Day. | 2022 2023 2024 2025 | People and Communications Teams | X |  | X |  | X |  | X
Review shortlisting and appointment processes to remove unconscious bias. (Pillar 1 - Employment Practices - Attract greater diversity in candidates through recruitment processes across all work groups) | Complete | The review of shortlisting and appointment processes to remove unconscious bias was completed in 2023, however we continue to monitor in an ongoing manner. The People Team uphold the following during shortlisting and appointment processes to ensure unconscious bias is eliminated. · Panel members are required to disclose any conflict or potential bias prior to commencing the shortlisting process. · Panel members are responsible for being aware of potential bias by themselves or other panel member throughout the process. If identified the panel member must raise the concern of bias with the panel for discussion. If required advice should be sought from the GM to ensure any bias is eliminated from the recruitment and selection process. · Interview panels are to be diverse in terms of gender, background, age, ethnicity and ability · On confirmation of acceptance by the preferred applicant the People team will prepare an appropriate contract of employment and forward it to the successful applicant inclusive of all relevant new employee paperwork and pre-employment requirements prior to commencement. · All LMW job advertisements list our Equity and Diversity Statement LMW's Senior Manager Talent and People Experience and Diversity and Inclusion Officer have engaged with an external organisation to educate all staff of LMW to recognise how unconscious bias tied to race, disability and mental health. During consultation with the external training organisation, it became evident that breaking the biases into individual modules would better help our staff to understand and appreciate what unconscious bias is, and how it impacts all our interactions daily. HR Generalist when starting a new recruitment process reviews the position and ensures the interview panel will be gender neutral. | LMW has a detailed Recruitment and Selection procedure that is adhered to and it ensures greater diversity within our recruitment processes by requiring: · Gender-balanced shortlisting panels and interview panels - this reduces the risk of personal bias by challenging any assumptions made by other members. · Interviews are conducted with a panel of two or three with a gender balance and diversity across tenure, skillset, and backgrounds, to minimise bias in the interview process. · Standardised interview questions are developed prior to short-listing to tailor each recruitment process to ensure hiring managers make decisions on skillset rather than personal biases. | 2023 | Senior Manager Talent and People Experience, Diversity and Inclusion Officer | X |  | X |  | X |  | X
Review current recruitment process to ensure that strategies, policies and procedures are free from gender bias and support equal pay and cultural safety (Pillar 1 - Employment Practices - Attract greater diversity in candidates through recruitment processes across all work groups) | Ongoing | LMW's People Team have reviewed all associated processes to ensure that strategies, policies and procedures are free from gender bias and support equal pay and cultural safety and will be an ongoing process. 15 June 2021 - Reviewed and updated document, reflecting position name changes and alignment with LMW's Talent Management framework. Further review was undertaken and the document updated 23 June 2022. A GIA was completed on LMW Recruitment and Selection procedure; the People Team revised and updated all recruitment documents, incorporating additional demographic fields to enable future reporting and monitoring of progress towards gender diversity and equity. HR Generalist, Diversity & Inclusion Officer and Engagement Officer regularly come together as a working group to review and ensure strategies, policies and procedures are free from gender bias. Quarterly internal gender pay gap calculations have been implemented since the end of the current reporting period as an additional monitoring tool. . LMW's new Governance Framework is being actively implemented and will further enhance monitoring. | (It should be noted at this point that we had been striving for further improvements to reducing the gender pay gap over the reporting period and were confident we would have seen a small positive change between the two reports. In implementing a quarterly internal gender pay gap calculation and preparing our GEAP progress report within the portal, it became apparent that the 2021 total remuneration figures submitted and published for LMW were incorrect. Please refer to the indicators tab for further explanation.) | 2022 2023 | People Team | X |  | X |  | X |  | X
Review opportunities to offer scholarships for females in non-gender typical roles e.g., engineering (Pillar 1 - Employment Practices - Attract greater diversity in candidates through recruitment processes across all work groups) | In progress | The Mallee Regional Innovation Centre approached LMW to offer a placement opportunity through the Invergowrie Scholarship. The scholarship is offered to female students who are studying in the Environmental Engineering space and was created to promote women in STEM careers. As at time of this report, a Melbourne University Scholarship recipient student is currently on placement at LMW. This scholarship was awarded to a female in non-gender typical roles - in this case, environmental engineering/chemical engineering. Between Dec 2022 and June 2023 LMW developed a People Strategy outlining 10 initiatives to be delivered across 18 months to support LMW achieve its strategic objective of having a high performing, engaged, diverse and inclusive workforce An initiative from the People Strategy is to establish a graduate and internship program in 2024. This strategy has been endorsed by LMW's Board and Executive Leadership Team. Additionally, on 14 December 2023 - LMW advertised on LMW socials communicating the great opportunity of our Apprenticeship/Traineeship Program (Mildura based). - Traineeships - Traineeships are offered in a range of areas within our organisation. We run our traineeship programs for a minimum of 2 years and offer Certificate III and IV in Business Administration, Work Health and Safety, Recordkeeping and Civil Maintenance. - Apprenticeships - We offer apprenticeships in our Electrical and Mechanical teams. Apprentices learn onsite from experienced tradespeople and attend trade school to gain theoretical knowledge and skills. Apprenticeships generally run for 3 to 4 years, depending on the training requirements. We encouraged expressions of interests from all people, actively promoted with careers counsellors that we are seeking to utilise this strategy to get traction in enhancing diversity, and are dedicated to inclusivity – regardless of gender identity, ethnicity, sexual orientation, ability or age. | Katya was selected as the successful applicant to join LMW's Water Quality and Environment team. Katya has been working with LMW for 8 weeks learning about how Lower Murray Water organisation delivers clean water and the operational tasks that are performed day by day. Engagement Officer and Snr Manager Talent & People Experience have commenced the development of a graduate program; an action plan and associated Gantt chart is in place and milestones to date have been reached. LMW's Project Team and Water/Environmental Quality team have been identified as the most suitable hosts. | 2023 2025 | People and Communications Team | X |  | X |  | X |  | X
Develop a framework for succession planning and talent identification to support equitable career development (Pillar 1 - Employment Practices - Develop and retain a diverse workforce) | Ongoing | The framework for succession planning and talent identification to support equitable career development was implemented in January 2022. Critical Positions are identified for each division of Lower Murray Water (LMW) by the respective General Manager and reviewed and approved by the Executive team on an annual basis. The People team prepare an annual Leadership and Talent Management paper to the Executive team and the Governance People and Culture Board Committee. The report will provide an overview of employee engagement in the PDP online system, an assessment of workforce succession and achievements in the past 12 months of employees achieving identified performance and development goals and career progression. Where gaps are identified in LMW’s completed succession planning report identifying skill sensitivities across LMW's operations the executive team will discuss other mitigation strategies to work toward redundancies existing to all critical positions within the organisational structure. | The succession planning report can be updated at any time throughout the year if circumstances change for identified employees and they are no longer considered suitable or available for a critical or pathway position they are identified for. 2023 Update: The initial succession planning was completed in 2022 however the ongoing monitoring and identification of opportunities are ongoing. We have therefore changed the status from Completed to Ongoing. | 2022 | People Team | X |  | X |  | X |  | X
Implement a Talent Management Framework (Pillar 1 - Employment Practices - Develop and retain a diverse workforce) | Complete | The pilot program commenced on 1 July 2021 and was completed on 30 January 2022 with the main objective of the pilot program to test the functionality of the Professional Development Plan (PDP) online system and ensure it was fit for purpose in readiness for the full launch on 1 February 2022. This objective was achieved, with positive feedback confirming the PDP online system was ready for full implementation. The process generated positive and proactive discussion between manager and employee. 2023 Update - The PDP process was amended during the reporting period to 3 review periods throughout the year (instead of 4). | The full launch was delivered on time with 81% employees formalising their PDPs by 1 March 2022. A range of support activities were implemented to support managers and employees in the development of their first PDP and include: • a dedicated resource and point of contact in the People Team to facilitate support, encouragement, and advice • online group sessions where managers and employees could dial in and ask questions, seek clarification, or request additional goals to be added to the drop-down lists to ensure they met their specific needs • one-on-one support with managers and/or employees to support the development of PDPs or support employees to review their draft PDP and prepare for a discussion with their manager • workshops with teams sharing a sample experience as an exercise to hear real feedback and providing an opportunity to learn from each other • instructional videos and a dedicated intranet page to provide hints, tips, and updates. | 2022 | Executive Team People Team | X |  | X |  | X |  | X
Implement Succession Planning Procedure (Pillar 1 - Employment Practices - Develop and retain a diverse workforce) | Complete | January 2022 LMW Succession Planning Procedure was implemented and communicated to LMW people leaders, the implementation of the procedure was developed by the Manager of People and Communications and is led by the Exec Team. The purpose of the Succession Planning Process was developed to improve Lower Murray Water’s (LMW) ability to ensure business continuity of people resources, mitigate against potential critical business operational gaps and provide career pathways for existing talent within the organisation. This process applies to all LMW people leaders and is led by the Executive team. | LMW reports show the below were identified in 2022: • 89 critical positions • 87 successors identified • 17 Career Pathway Positions A deep look in to the analysis of LMW successions plans, showed the following data per work group: (these are number of Successors identified for critical position per business unit) - Business Services and Performance - 9 - Infrastructure Services - 22 - People and Stakeholder - 10 - Service Delivery & Operations - 46 Infrastructure Services and SD&O are two areas where there is greatest potential to utilise the succession planning to increase the representation of women in our workforce. This is a focus for our recruitment campaigns in 2024 | 2022 | Executive Team People Team | X |  | X |  | X |  | X
Educate staff on recruitment and promotion processes (Pillar 1 - Employment Practices - Develop and retain a diverse workforce) | Ongoing | Increasing Leadership capability across LMW is a key focus and this includes supporting leaders to develop meaningful PDP's with their employees and enable employees to identify clear career paths across the organisation. The People Team and Communications team work closely together to educate staff on recruitment and promotion processes and build confidence in the fairness and transparency of process and opportunity. LMW People and Safety Officer and HR Generalist conduct workshops to support leaders and employees have confident understanding how to start and complete their appraisals within their PDP. These workshops are ran face to face and online for our staff in other regions. Instruction guide regarding LMW PDP's are published on our internal intranet website. Development goals including: * Providing opportunities for employees to join interview panels to learn and understand recruitment processes * Provide opportunities for employees to take on Acting positions during periods of leave are readily used to support the development and education of our staff on LMW recruitment and promotion processes LMW uses Expressions of Interest (EOI) processes for Acting positions where the position is vacant, this supports educating employees on potential career progression opportunities and provides all employees to consider these opportunities. Recruitment and promotion processes are also published on LMW Intranet to advise employees new opportunities, positions are open | In 2023 LMW rolled out the People Strategy, and at the launch all staff heard of firsthand accounts of colleague’s pathways into and within LMW. This was followed by a second Connecting event in December 2023 where we focused on our priorities for 2024, recognising our achievements of 2023 and hearing from two employees about their career journey's at LMW. | 2022 2023 2024 2025 | People and Communications Team | X |  | X |  | X |  | X
Celebrate internal promotions throughout LMW (Pillar 1 - Employment Practices - Develop and retain a diverse workforce) | Ongoing | Celebrating internal promotions throughout LMW is an ongoing action, we recognise employee promotions, secondments and acting opportunities to further their learnings in our organisation LMW distribute a weekly communication update to all staff via the communications team and this includes internal appointments and recognises employees taking up secondment and acting opportunities to further their learnings. LMW has achieved its target of 50% of vacancies filled internally by June 2023 ahead of the planned June 2025 timeframe | Fortnightly 'Channel Meetings' have been held in 2023 and are set to continue in 2024. Standing agenda item congratulates all internal appointments and secondments, as well as introducing new staff to LMW. 80% of internal staff movements within the reporting period 22/2023 were communicated on the LMW intranet page to recognise and celebrate their promotions within the workplace | 2022 2023 2024 2025 | People and Communications Team | X |  | X |  | X |  | X
Develop and implement staff retention interviews (Pillar 1 - Employment Practices - Develop and retain a diverse workforce) | In progress | This strategy was implemented in September 2021 focussing on newer employees. The need for this focus was verified when at June 30 2023 we had a staff turnover rate in excess of 24%. 25% of the staff who exited the organisation in the previous 12 months had less than 2 years tenure. With a review of the New Employee - Induction and Review Process developing and implement staff retention interviews were designed into three reviews held from the People Team and LMW Employee manager. In 2024 we have added a fourth touch point in the form of 6 month pulse check with the People Team. - 2 & 5 Month Manager Review - New employees and Internal transfers - 3 Month Pulse Check - New employees and internal transfers PDP (Professional Development Plan) Appraisals - 3 x mid-year appraisals - final review | Within the reporting period 2022/2023 data shows LMW People team conducted 32 pulse check interviews and 53 to date in 2023. This is with new employees to the organisation and internal movements. | 2022 | People Team | X |  | X |  | X |  | X
Enterprise Bargaining Agreement classification review to ensure transparency of equal pay for equal or comparable value across all levels of the workforce Pillar 1 - Employment Practices - Conduct annual gender pay gap audits to identify where pay gaps exist and why) | In progress | A draft Salary structure has been prepared for negotiation in 2024 for the 2025 EA. A Remuneration (REM) strategy is under development to articulate the full range of benefits available to employees working with LMW. The People strategy included an EVP "Our People, Our Purpose' | As at time of report, this is in early stages of development | 2023 2024 2025 | People Team EBA Committee | X |  | X |  | X |  | X
Develop targets and strategies to address gender pay gaps (Pillar 1 - Employment Practices - Conduct annual gender pay gap audits to identify where pay gaps exist and why) | In progress | This action is currently in progress with the development of an LMW Remuneration (REM) Strategy, which will provide more structure and equity to the distribution of remuneration. The REM will form part of a multi-pronged approach to reducing the Gender Pay Gap at LMW. LMW's Target Operating review was undertaken in 2022 by an external consulting firm, and the current Executive Leadership Team is committed to delivering on recommendations which would maximise workforce utilisation and create opportunities to improve equity and inclusion resulting in a gender pay gap reduction. | As at time of report, this is in early stages of development | 2022 2023 2024 2025 | Executive Team People Team | X |  | X |  | X |  | X
Develop parental leave policy that supports transition back to work through flexible working arrangements for both primary and secondary carers and mentoring programs (Pillar 1 - Employment Practices - Implement approaches to build a flexible workplace that supports employees to balance work and life responsibilities) | In progress | Currently in progress in consultation with LMW current Enterprise Agreement Committee 2024 has been added for completion of this action | Through EA negotiations for the current agreement LMW increased and strengthened Parental leave entitlements and eligibility to include same sex partners and a father's entitlement to parental leave. Development of a broader policy to support planning and transition to and from parental leave is underway. Our 2023 data shows a significant increase in the amount of parental leave taken regardless of gender. We have also seen a marked uptake of part-time arrangements by male employees to better support their young families | 2023 2024 | People Team ID&E Committee | X |  | X |  | X |  | X
Train managers in the use of the Parental Leave Policy and Flexible Work Arrangement Policy in order to inform staff about and discuss access to flexible work arrangements (Pillar 1 - Employment Practices - Implement approaches to build a flexible workplace that supports employees to balance work and life responsibilities) | Ongoing | During 2023 LMW Flexible working arrangements, including the associated policy were reviewed. LMW's Flexible Work arrangements and remote work policies have been combined into a Hybrid Work Policy and Procedure. This policy supports a broader range of modes of work including arrangements that support transition to retirement and return from parental leave. It also facilitates negotiating HWA during the recruitment/onboarding phase or at any time during an employee's tenure with LMW. The People team will conduct workshops in 2024 to train managers in the use of the policy in order to inform staff and discuss the opportunity to access to hybrid work arrangement. All employees who have a current Flexible work arrangement (FWA) in place will need to renegotiate this in the new application and complete a current Risk and OHS assessment. It is requested that this occur in the first quarter of 2024 with all existing FWA’s replaced with a new Hybrid work arrangement by the end of March 2024. | As per above, 2023 data shows an increase from 2021 data on the amount of parental leave taken, as well as an increase in the number of individuals who have a Flexible Work Arrangement | 2023 2023 | People Team | X |  | X |  | X |  | X
Create an internal campaign to promote and encourage flexible working including discussions as part of induction of new staff (ensuring on-call staff are included) (Pillar 1 - Employment Practices - Implement approaches to build a flexible workplace that supports employees to balance work and life responsibilities) | In progress | This action was implemented in March 2021, coinciding with the return to office post COVID | The number of formal flexible work arrangements (FWAs) have risen significantly, from just 6% of the workforce in 2021, to one in four employees having a formal FWA in place in 2023. Of the one in four employees who have a formal FWA in place, 38% are men which is more than double the 2021 figure of 17%. As highlighted previously; improvements in equality, diversity, and inclusion benefit everyone, including men. | 2023 2023 | Leadership Team People and Communications Team | X |  | X |  | X |  | X
Promote and profile flexible arrangements for all genders within LMW and throughout the broader community (Pillar 1 - Employment Practices - Implement approaches to build a flexible workplace that supports employees to balance work and life responsibilities) | Ongoing | The new Hybrid Work Arrangements focus on how to foster collaboration through Hybrid Work Arrangements, creating greater flexibility to help employees maintain work-life balance. It confirms the continued commitment of LMW to finding practical solutions to help maintain a work/life balance. We consider all requests on a case by case basis and look to balance our operational requirements with the needs of our employees, stakeholders and team members. Types of Hybrid Work Arrangements may include: - Flexible start and/or finish times; - Days of work, such as part-time work or compressed full-time hours; - Patterns of work, such as job-sharing arrangements; and - The location of work, such as working from home or another location. | As per above. | 2022 2023 2024 2025 | People and Communications Team | X |  | X |  | X |  | X
Promote increased carers and secondary carers leave as per LMW's 2021 Enterprise Agreement within the organisation (Pillar 1 - Employment Practices - Implement approaches to build a flexible workplace that supports employees to balance work and life responsibilities) | In progress | LMW's 2021 Enterprise Agreement The Agreement was approved and, in accordance with s.54 of the Act, operated from 12 January 2022. Provisions were improved, now managers actively work with employees to ensure appropriate leave practices are in place and utilised to support employees in managing their work-life balance and wellbeing. | During the review of LMW Flexible working arrangements and FWA policy in 2023 GM People and Stakeholder consolidated various documents to a single LMW Hybrid Work Policy. This reduces complexity of the support systems. The People Team will be instrumental in 2024 in ensuring all staff are aware of the consolidated policy and supporting arrangements, and during these consultations the People Team will promote increased carers and secondary carers leave as per LMW 2021 Enterprise Agreement. In 2021: 29 women and 50 men accessed carers leave. In 2023: 36 women and 63 men accessed carers leave. | 2022 | People and Communications Team | X |  | X |  | X |  | X
Improve onboarding documentation to reflect questions from PMS Intersectionality Report and encourage existing staff to update their information (Pillar 2 - Reporting - Ensure staff diversity and intersectionality information is correctly captured and reported on) | In progress | LMW undertook a detailed review of it onboarding program for new staff and internal movements in late 2022 and early 2023. As a result of this review a new program has been developed which includes the first 3 months being focused on the position the employee has within the organisation and getting to know their team. The second 3 months is focused on learning how their position and team interacts with the broader business and understanding whole business operations. The new onboarding program comes into effect from January 2024. As part of the new program LMW onboarding documentation have been reviewed and are being updated to enable the organisation to capture the increased demographic details (and allow for intersectionality assessment in future years). LMW does not yet have the technical system capacity to manage this data electronically, so it is a rather labour intensive manual process that must be maintained until such time as funding and IT solutions can be assigned. The People team are maintaining these sensitive personal details in the meanwhile, ensuring anonymity is preserved when reporting and utilising the data to improve outcomes. Diversity and Inclusion Officer will communicate to all staff the update on the new Employee Personal Information form in the early months of 2024 for existing staff to update their information. | 2023 data reported in the reporting platform came from a mix of employee data available in payroll/finance system, content manager (record management system) and restricted access spreadsheets maintained by the People Team. It is likely that this multiple storage location will need to be maintained for the next reporting period as the required enhancements are not currently in scope of the Business Transformation Program (BTP) (enhancing our IT systems). | 2022 2023 +2024 | People Team | X |  | X |  | X |  | X
Report on a broader range of intersectionality representation including gender, Aboriginality, age, disability, ethnicity, gender identity, race, religion, sexual orientation and other attributes (Pillar 2 - Reporting - Ensure staff diversity and intersectionality information is correctly captured and reported on) | In progress | Delays to LMW's Business transformation program have delayed progress in this area, however the relevant planning has been undertaken to support this reporting and where possible manual processes have been undertaken to collect data required to enable proactive monitoring and strategic planning to increase participation across the broad scope of intersectionality LMW Diversity & Inclusion Officer has developed a new Employee Personal information form with diversity declaration added that will be implemented in early 2024 as part of the new onboarding process | With current delays of LMW's BTP, LMW's Diversity and Inclusion Officer has engaged with the IT team to develop a tailored report on the appropriate criteria to develop the LMW Monthly/Quarterly GEAP Report. As this is still a manual process developing the report has minimised the initial time to complete by half. LMW Business transformation program will restart in early 2024 and the People Team will continue to strive for enhancements to the system that will enhance confidentiality (and therefore confidence in disclosing/reporting) and allow for greater digital demographic data monitoring. | 2022 2023 +2024 | People Team ICT Team |  |  |  |  | X | X
Create specific categories within CiA that directly align with the Victorian Gender Equality Commission’s Workplace Gender Audit (Pillar 2 - Reporting - Ensure staff diversity and intersectionality information is correctly captured and reported on) | In progress | Delays to LMW's Business transformation program have delayed progress in this area, however the relevant planning has been undertaken to support this reporting and where possible manual processes have been undertaken to collect data required to enable proactive monitoring and strategic planning to increase participation across the broad scope of intersectionality. An issue that has been detected in the past 6 months is that as the system is essentially a finance based system, there is limited ability to store sensitive personal details in a truly confidential manner. Work will continue in the refreshed BTP in 2024 and 2025 to enable greater self-management of data for individual employees - this will be impacted by the issue detected above (governance of sensitive information), however, there is a back up plan involving the People team continuing to maintain the sensitive information. | As of January 2024, and as mentioned in the adjacent cell, this is an ongoing project that involves the People Team, the BTP and IT teams, and is planned for implementation across the next 18 months. There is every possibility a bespoke system will need to be considered should the InTech/TechOne solutions currently embraced by LMW not be compatible with the ongoing secure storage and auditable access of sensitive personal information. | 2022 +2023 +2024 | People Team ICT Team |  |  |  |  | X | X
Continually promote the support of the People Team, HSR’s and the Executive to encourage employees to discuss experiences and concerns confidentially and educate staff on the options for reporting (Pillar 2 - Reporting - Guarantee that sexual harassment reporting processes are completed correctly to ensure an accurate understanding of the workplace environment) | Ongoing | As previously reported, the Rapid Global incident reporting system was not restricted in access sufficient to endorse the use as a sensitive incident/hazard reporting repository. Sensitive reports such as sexual harassment complaints, and other staff-grievances needed to be manually maintained by line managers and the People team (fortunately there have been very few of these in previous years). LMW has committed to enhancing the confidentiality and robustness of its information systems, in 2023 the Safety Team implemented Beakon (Safety, Risk & Compliance System) turning off our Rapid Global system previously used. Internal testing and user guidance is currently being developed to ensure the reporting of sexual harassment and other sensitive staff matters can be safely recorded and managed within the system. LMW is meeting with Beakon early 2024 to ensure this is possible. | Awareness training regarding Sexual Harassment and Sex Based Discrimination was held at the end of 2023 for the People Team, and all people leaders within LMW must undergo mandatory training in the same subject in March 2024. This training is provided by a partner of Colin Biggers & Paisley Lawyers. General staff awareness of positive duty has commenced in December 2023, with a focussed campaign planned post the March training. | 2022 2023 2024 2025 | People Team Leadership Team OHS Committee |  |  |  |  | X | X
Develop internal, confidential OHS reporting for sexual harassment incidents (Pillar 2 - Reporting - Guarantee that sexual harassment reporting processes are completed correctly to ensure an accurate understanding of the workplace environment) | In progress | LMW committed to a new dedicated position of Senior Manager Health and Safety, and this role was filled in Feb 2023. After analysing our current safety system Senior Manager H&S discovered Rapid Global was an insecure safety reporting system and started the process of consulting with software developers. After consultation Senior Manager Health and Safety presented a business case to implement Beakon as LMW's new safety system. Beakon provides reducing risk, improving safety and managing compliance within the software. As previously reported, the Rapid Global incident reporting system was not restricted in access sufficient to endorse the use as a sensitive incident/hazard reporting repository. Sensitive reports such as sexual harassment complaints, and other staff-grievances needed to be manually maintained by line managers and the People team (fortunately there have been very few of these in previous years). LMW has committed to enhancing the confidentiality and robustness of its information systems, and in late Nov 2023 the Safety Team implemented Beakon (Safety, Risk & Compliance System) turning off our Rapid Global system previously used. Internal testing and user guidance is currently being developed to ensure the reporting of sexual harassment and other sensitive staff matters can be safely recorded and managed within the system. LMW is meeting with Beakon early 2024 to ensure this is possible. | The People Matter Survey conducted in 2023 indicated there are improvements to be made in staff confidence in health and safety mechanisms in pockets of the organisation. Department managers met and discussed the results and instigated actions to address the disparity across departments. Safety culture pulse check conducted in December 2023 showed a significant improvement in employee confidence in the organisation's commitment to employee health and wellbeing, and increased confidence in the systems implemented in the past 10 months. Employee inductions are now facilitated by Beakon as at time of reporting, and work is underway in enhancing the confidence in using the system as a reporting repository for sensitive/confidential matters including sexual harassment incidents and investigations. | 2023 +2024 | People Team Leadership Team OHS Committee |  |  |  |  | X | X
Commit to reporting on sexual harassment complaints to the LMW Board as a standing agenda item in the HR report (Pillar 2 - Reporting - Guarantee that sexual harassment reporting processes are completed correctly to ensure an accurate understanding of the workplace environment) | In progress | This is under development as at time of reporting, in line with the entry above. The Board are currently informed of emerging risks, and this would include sexual harassment reports/concerns, although it isn't currently recorded that there are 'nil to report' sexual harassment incidents. This is planned for 2024 board reporting. | (As described above. Future evidence will be in the form of Board Reports) | 2023 +2024 | People Team |  |  |  |  | X | X
Form a working group to brainstorm, consult and create a set of values that reflect LMW's views and behaviours (Pillar 3 - Workplace Culture - Develop and implement a set of internal values that foster a diverse and positive workforce culture) | Complete | A working group of 7 members of the ED&I Committee was formed in September 2021 and an action undertaken to review the applicable LMW Values at the time, and 'Behaviours of Growth'. Feedback and ideas from the ED&I Committee were incorporated into the People Strategy consultation process where the new LMW Values were developed and finalised. Through the implementation of the People Strategy, the revised organisation values and employee value proposition will be realised. | The finalised organisational values are: Respect - We celebrate uniqueness and provide an inclusive culture for all Grow - We strive to continuously develop, learn and grow both individually and as an organisation Collaborate - We are a collaborative workplace that provides a supportive, friendly working environment Deliver - We strive to deliver the best service to our community and ensure they have secure and reliable water and waste management services Safe Work Done Well - We promote a Safety culture which prioritises physical and mental health and wellbeing | 2022 | ED&I Committee | X |  |  |  | X | X | X
Promote internal values throughout the organisation through face to face training on acceptable behaviours (Pillar 3 - Workplace Culture - Develop and implement a set of internal values that foster a diverse and positive workforce culture) | In progress | LMW undertook a detailed consultation process between December 2022 and June 2023 in the development of a People Strategy, review of organisational values and the development of an Employee Value Proposition. The People Strategy including new organisational values and EVP was launched in July 2023 with a Lunch and Learn event for all staff in Mildura Main office and Swan Hill office. A detailed implementation plan has been developed to ensure delivery of the People Strategy over 18 months from July 2023 to December 2024.Through the delivery of pillar 2 of the People Strategy 'Making LMW a Rewarding Place to Work' employees will engage in connecting activities, to share knowledge and experiences and identify the ways we each connect with our Values. | People Strategy - Lunch and Learns LMW General Manager People & Stakeholder held the first session, during this session all employees came together to listen and view what the LMW People Strategy is and how we can demonstrate our Organisational Values. The People Team have implemented the Organisation Values on internal documentation and external job ads | 2022 | Leadership Team ED&I Committee | X |  |  |  | X | X | X
Share a collection of internal communications throughout each year to promote diversity across gender, Aboriginality, age, disability, ethnicity, gender identity, race, religion, sexual orientation, and other attributes (Pillar 3 - Workplace Culture - Educate our employees on gender and intersectional diversity to we create an environment that is safe for all people to bring their authentic self to work) | Ongoing | As part of educating our employees on gender and intersectional diversity to create an environment where all can be themselves, our Engagement Officer and Diversity and Inclusion (D&I) Officer meet on a regular basis to share and develop internal communications through the year. LMW has created an internal Events Poster that identifies one event per month that allows LMW to celebrate, recognise and create further awareness of diversity and intersectionality. Welcome to Country and Acknowledgment of Country Protocols: When implementing the LMW Acknowledgement of Country guidance cards our Engagement and D&I Officers shared the importance and relevance of showing respect to Aboriginal and Torres Strait Islanders through the practices of either facilitating a Welcome to Country and/or undertaking an Acknowledgment of Country. Educating our staff on the difference, their purpose and the need for sincerity when undertaking has increased employee awareness and forms a key part of all meetings held internally and externally. Referendum 2023 Our General Manager People & Stakeholders issued an email to all staff advising of the Voice to Parliament and reminded all staff that we should demonstrate the public sector value of respect regardless of our personal opinion, and reiterated our Code of Conduct. Connecting with First Nations People - All staff training Embracing cultural awareness can help us recognise how cultural differences can influence one’s perceptions, helping us become more accommodating of different opinions. In addition, being empathetic and understanding can help create an inclusive environment that encourages creativity and innovation, while improving efficiency and profitability. Diversity & Inclusion Officer and Senior Manager Talent and People Experience engaged with external training organisation genU to enrol LMW staff into Connecting with First Nations People. The module developed was designed to build employee's confidence to work respectfully and effectively with Indigenous Australians, and to increase their understanding of the importance of promoting the integration of Indigenous and non-Indigenous Australians to achieve equality and the benefits that follow. People Strategy: Lunch and Learn The career journey stories that are developed for social media are also shared internally and through the Lunch and Learn connection events we hear from 2-3 staff at each event about their career journey both into and within LMW. | Connecting with First Nations People - All staff training - as at time of report, 219 staff have been enrolled into the self-paced learning package since December 2023, and our reports show 164 staff have completed the training. Feedback on the nature and content of the training has been extremely positive, with some staff celebrating their learning on social media and sharing their personal insights. | 2022 2023 2024 2025 | People and Communications Team | X |  |  |  | X | X | X
LMW will commemorate and celebrate cultural and awareness events such as NAIDOC Week, Harmony Day, White Ribbon Day, Pride Month, International Woman’s Day (Pillar 3 - Workplace Culture - Educate our employees on gender and intersectional diversity to we create an environment that is safe for all people to bring their authentic self to work) | Ongoing | As part of educating our employees on gender and intersectional diversity to create an environment where we can all be our true selves, our Engagement and D&I Officers meet on a regular basis to share and develop internal communications through the year. This is then shared within the ED&I committee to lead the participation in commemorating and celebrating cultural awareness. | NAIDOC Week - For our Elders 2023 LMW held celebrations Monday 3 July 2023 at our Mildura Office: Representatives from The First Peoples of the Millewa Mallee joined us to deliver an Acknowledgment of Country and Smoking ceremony, this was shared via live stream with all LMW sites. Mildura Rural City Council Walk against Family Violence for White Ribbon Day Friday 17 November 2023 - Langtree Mall to Power House. Attended by a cross section of the organisation, from all departments, genders, positions, ages and nationalities. Internationals Women's Day At LMW we celebrate IWN in many different ways to share the creativity our female workers bring each and every day. We profiled and asked them why IWD is important to them, their future goals and what inspires them - we then shared this across LMW internally and externally via social media Engaged with a local organisation - The Mallee Sexual Assault Unit and Mallee Domestic Violence Services provide services for women, men and children throughout the Northern and Southern Mallee region, border communities of New South Wales, the Mallee Track and Shires of Gannawarra and Buloke. LMW conducted a fundraiser donating essential items for their clients. This resulted in a very large donation of supplies from both Mildura and Swan Hill offices. Pride Month We encouraged al staff to wear a colour of the rainbow, with the idea to take an all-staff photo emulating the LGBTQIA+ rainbow flag. This was achieved and the photo elicited significant interaction on social media. A significant aspect of pride month is self-expression. This was a great initiative that brought allies together from all cultures, ages, genders and identities. 16 Days of Activism To mark the 16 Days of Activism and Respect Is campaign, LMW hosted a breakfast to raise awareness and funds for local Mallee Sexual Assault Unit and Domestic Violence Services and Mallee District Aboriginal Service - Meminar Ngangg Gimba which provides crisis accommodation for those experiencing family violence. Staff were involved in the campaign, on the morning of the shared breakfast we supplied rocks to paint with the theme of ‘what respect means to you’. We encouraged the use of the colour orange as it is a colour of significance to the 16 Days of Activism and Respect Is campaign. | 2022 2023 2024 2025 | ED&I Committee | X |  |  |  | X | X | X
Support the use of gender pronouns in staff email signatures (Pillar 3 - Workplace Culture - Educate our employees on gender and intersectional diversity to we create an environment that is safe for all people to bring their authentic self to work) | Ongoing | Our Diversity & Inclusion Officer developed communications to educate the staff on What a Pronoun is and the importance of using them. Supporting the use of gender pronouns in staff email signatures will be an ongoing action within LMW | Educating information sent to all staff showing the importance of a pronoun and what they are. Members of the EDI Committee also participated in a Respect, Culture & Diversity: Allyship Training webinar presented by Sally Goldner to learn how to create an equitable and inclusive workplace and become a better ally, during this webinar the importance of pronouns was discussed and gave us better understanding and knowledge to pass the information on to workgroups. | 2022 2023 | Leadership Team All Staff | X |  |  |  | X | X | X
Develop a framework to ensure all policies and procedures are gender neutral (Pillar 3 - Workplace Culture - Educate our employees on gender and intersectional diversity to we create an environment that is safe for all people to bring their authentic self to work) | Complete | The Governance Team have developed two new frameworks to guide LMW about its governance requirements this action was implemented September 2023 Governance Operating Model: A Framework for Corporate Governance LMW’s new Governance Operating Model describes the governing regulatory environment in which LMW operates, the requirements and obligations we are bound to and supports the achievement of LMW’s goals while ensuring legal and ethical compliance. Aimed at staff as the end-user, this framework provides guidance as to how frameworks, policies, procedures, and supporting documents will be developed, approved, communicated, and reviewed at LMW. | LMW have developed a new Governance Framework which has been endorsed by the Board and is now in implementation. This framework includes a checklist to identify which policies and procedures require a GIA and future system enhancements will ensure a policy or procedure cannot be approved without an assessment to determine if a GIA is required. | 2023 | Governance Team | X |  |  |  | X | X | X
Champion 6.4 of the VPSC Code of Conduct, "Equality and Diversity", through internal communications to all staff (Pillar 3 - Workplace Culture - Promotion of the Public Sector Value of Respect, within the Code of Conduct for Victorian Public Sector) | Ongoing | Internal communications from our Engagement Officer and Diversity and Inclusion Officer are shared through LMW internal platforms. Internal communications are also held within LMW Lunch and Learn sessions held by members of the Executive Team and Managing Director | At the last lunch and learn 2 participants undertaking a Leaders wellbeing development program to increase capability in supporting employee wellbeing and psychological safety shared their key learnings so far and all participants are now starting to act as champions across the business. As part of championing 6.4 of the VPSC Code of Conduct, LMW are facilitating a trial over 12 months which consists of a mentoring program for a selection of leaders to build leader capability in managing employee wellbeing, and enhancing psychosocial safety awareness. This program is underway and 14 Leaders / future leaders are participating. | 2022 2023 2024 2025 | Communications and Engagement Teams | X |  |  |  | X | X | X
Engage senior leaders in the delivery of RAP commitment (Pillar 3 - Workplace Culture - Create and implement a Reconciliation Action Plan (RAP) to foster an appreciation of Aboriginality and cultural and ethnicity diversity with LMW) | In progress | Through research we understand that when organisations achieve gender equality at the executive level, they are more likely to be successful at achieving diversity and inclusion at all levels of the organisation. Through the recruitment of a new Executive Leadership Team (ELT) in December 2023, gender equality was a key component of the recruitment campaign and appointments made have resulted in a 50/50 split of women and men members. | Achievements in December 2023 have set LMW for success in the 2023-2025 reporting period. | 2022 2023 2024 2025 | People and Communications Teams | X |  |  |  | X | X | X
Communicate our commitment to reconciliation to all staff internally through cultural sharing (Pillar 3 - Workplace Culture - Create and implement a Reconciliation Action Plan (RAP) to foster an appreciation of Aboriginality and cultural and ethnicity diversity with LMW) | Ongoing | The initial activities were completed as per the plan. Subsequent review of the GEFAP identified this needs to be an ongoing commitment to sustain and improve on current position. In 2023, we are changing the status to ongoing. In consultation of developing LMW RAP informative sessions were held in December 2021 to share "What is a Reconciliation Action Plan?". LMW’s journey to reconciliation formally started in 2019 with the development and endorsement of our first Reflect Reconciliation Action Plan. This initial action plan kickstarted the enhanced engagement and relationships with the local Traditional Owners of our service region and began the learning journey for our staff and board. LMW has been delivering the Victorian Murray Floodplain Restoration Project (VMFRP) and staff have seen first-hand the importance of the involvement of Traditional Owners in decision-making processes to protect cultural heritage and restore ecological value. | The preparation of our second Reflect RAP has helped our organisation identify the gaps in knowledge and opportunity for continued learnings from First Nations people. LMW recognise our important role as one of the stewards of water resources and the need to work closely with the community to share the cultural connections to our work. Our commitment to diversity, equality and inclusion has seen LMW embed Aboriginal and Torres Strait Islander values into our recruitment processes. Through the inaugural RAP, we implemented an identified Aboriginal and Torres Strait Islander position and successfully filled that position. | 2022 2023 | People and Communications Teams | X |  |  |  | X | X | X
Increase employee understanding of the purpose and significance behind cultural protocols, including Acknowledgement of Country and Welcome to Country (Pillar 3 - Workplace Culture - Create and implement a Reconciliation Action Plan (RAP) to foster an appreciation of Aboriginality and cultural and ethnicity diversity with LMW) | Complete | To increase LMW employee understanding of the purpose and significance behind cultural protocols, including Acknowledgement of Country (AoC) and Welcome to Country (WtC), LMW's Engagement and D&I Officers created communications on WtC and AoC protocols and distributed AoC Guidance cards to all staff. | Acknowledgment of Country Guidance Cards LMW's Engagement Officer, in conjunction with our Diversity & Inclusion Officer (who identifies as a proud Aboriginal woman) worked together to design and publish the LMW Acknowledgment of Country Cards. Three cards of the four were made to respect the lands of the Latji Latji, Wemba Wemba, Barapa Barapa Peoples. The fourth card published is the Acknowledgment of Country written by our Diversity and Inclusion Officer which can be used by individuals when they travel onto other lands. These cards can be (and are often) used at the beginning of meetings, speeches or an event. | 2022 2023 2024 2025 | People and Communications Team | X |  |  |  | X | X | X
Bystander training for all current employees and compulsory training for all new employees (Pillar 3 - Workplace Culture - Creating a zero- tolerance culture throughout LMW regarding workplace sexual harassment and gendered violence) | Not started | This is action was due to be completed in 2022, however, we identified that more foundational training needed to occur first before Bystander Training was likely to achieve the desired learning outcomes.. Awareness training in the following has occurred: First Nations Mental Health Awareness Disability Awareness Planned: Bullying & Harassment & Discrimination training is scheduled for February and March 2024. | Connecting with First Nations People - All staff training - as at time of report, 219 staff have been enrolled into the self-paced learning package since December 2023, and our reports show 164 staff have completed the training. | 2022 +2023 +2024 | People Team | X |  |  |  | X | X | X
Create a workplace sexual harassment and gendered violence prevention plan in consultation with employees and employee representatives (Pillar 3 - Workplace Culture - Creating a zero- tolerance culture throughout LMW regarding workplace sexual harassment and gendered violence) | In progress | Staff education and subliminal messaging has commenced since late 2023 in regards to sexual harassment, sex-based discrimination, and all staff have undergone gendered violence training (covered in the Domestic & Family Violence Awareness training previously mentioned) During 2023 we have moved from relatively insecure safety reporting system to an updated safety system implemented by LMW Senior Manager Health and Safety and Safety Team, consultation will be made with Beakon in the early year to discuss and incorporate sexual harassment within the system. | As LMW has a new safety system and awaiting consultation for sexual harassment interface, the action to create of a workplace sexual harassment and gendered violence prevention plan in consultation with employees and employee representatives will be held in the first quarter of 2024 with EDI & OHS Committee. As our Diversity an Inclusion Officer is the chair of EDI and the People HSR Representative this action will be an ongoing agenda item until completion with the monthly meetings of both committees. | 2023 +2024 | OHS Committee ED&I Committee | X |  |  |  | X | X | X
Handling sexual harassment challenging and confidential conversations training for all existing employees and compulsory training for all new employees (Pillar 3 - Workplace Culture - Creating a zero- tolerance culture throughout LMW regarding workplace sexual harassment and gendered violence) | Ongoing | All staff within LMW must undergo mandatory training regarding Bullying, Harassment & Discrimination (including Sexual Harassment) t in Feb-March 2024. This training is provided by a senior partner of Colin Biggers & Paisley Lawyers. General staff awareness of positive duty has commenced in December 2023, with a focussed campaign planned post the Feb-March training. An online learning module will be developed in 2024 to ensure learning outcomes from facilitated training, and will be included in all new employee induction packages. A further Proteus Leadership Development Program "Leading People & Culture" has been scheduled for May 2024. | Awareness training regarding Sexual Harassment and Sex Based Discrimination was held at the end of 2023 for the People Team 20 LMW People Leaders participated the Proteus Leadership development program "Leading People and Culture in June 2022. This training program supports leaders to develop skills in having challenging and confidential conversations. | 2023 2024 2025 ongoing | People Team | X |  |  |  | X | X | X
External communications contain photos of diverse employees in non-gender typical workgroups (Pillar 4 - Community Engagement - Promote LMW’s image and reputation as an inclusive organisation that supports and values diversity) | Ongoing | Social media posts were completed to promote the diversity of careers available at LMW and the Diversity of our workforce. Promoting people from different cultures, gender and ages. Attraction and retention with local Mildura Living magazine, published articles of staff from Lower Murray Water. | We have completed a range of social media posts to promote the diversity of careers available at LMW and the Diversity of our workforce. Promoting people from different cultures, gender and ages. We have also conducted an attraction and retention campaign through the local Mildura Living magazine where we have done a story of the careers of specific people including our female General Manager People and Stakeholders and one of our male Engineer,a refugee from Iraq | 2022 2023 2024 2025 | People and Communications Team | X |  |  |  | X
Employees from all backgrounds are celebrated throughout the community via multiple communication methods (Pillar 4 - Community Engagement - Promote LMW’s image and reputation as an inclusive organisation that supports and values diversity) | Ongoing | Cultural awareness helps promote inclusivity, respect and understanding within our communities, workplaces, and organisations. LMW continues advancing their community involvement to make our employees feel valued and respected | Throughout the year LMW celebrates many culturally important dates these are then shared on multiple social platforms internally and externally Internal celebrations within LMW are also held in our People Strategy Lunch and Learns, where we hear from our employees their background and inspiring stories | 2022 2023 2024 2025 | People and Communications Team | X |  |  |  | X
Celebrate the new 2021 EA Clauses externally (Pillar 4 - Community Engagement - Promote LMW’s image and reputation as an inclusive organisation that supports and values diversity) | Complete | In completion of the new 2021 EA, clauses were published on external websites and within the organisations | LMW Enterprise Agreement has been published on CPSU Victoria and FairWork Commission | 2022 | People and Communications Team | X |  |  |  | X
P4 - Community Engagement Strategy: Advance gender and intersectional equality as a shared responsibility across the broader community Partnerships are formed with relevant organisations and community groups to share knowledge and seek their expertise where appropriate | Ongoing | This action is ongoing The Victorian water industry Diversity Steering Committee will continue to meet on a quarterly basis to share knowledge and support progress against the commitments made within the EDI Water strategy. DISC will also identify and share best practice approaches and measures from all industries. The IWN Diversity & Inclusion Technology Program was established in 2022 to test and trial assistive technologies on behalf of the water industry and share learnings in a more inclusive environment. Learn more below about what we’re working on. The plan has also driven positive change in our organisation. By moving to skills-based appointments, we have seen a shift in female participation in our voluntary roles. Within the first 12 months of our plan, our Executive Group moved from 10% to 40% female participation, Program Managers from 0% to 40% and Champions are now at 44%. While diversity and inclusion is about more than gender, we are proud of this shift to better reflect our industry. We are working in alignment with other industry inclusion programs, such as WaterAble and Pride in Water, and we participate and promote activities, events and significant cultural dates. | LMW's GM People and Stakeholder is the Chair of Vic Water's Diversity, Equality and Inclusion Steering Committee and has lead this committee through the development of a new strategy for the water sector for 2024-2028. She also sits on the Executive Safety Group for Vic Water and the Executive Group for Intelligent Water Networks (IWN) including a project team working to identify and enable the use of technology solutions to support People who identify with a disability participate in the workforce. This includes noise cancelling headphones, accessibility tools for sight impairment and office equipment to enhance mobility. D&I Officer participates in regular IWN meetings, LMW will receive the Inclusion Toolkit in the early 2024 and will engage with LMW IDE Committee to support the use of the devices throughout the organisation | 2022 2023 2024 2025 | People and Communications Team
P4 - Community Engagement Strategy: Advance gender and intersectional equality as a shared responsibility across the broader community Participate in relevant networks and forums | Ongoing | Participation in relevant networks and forums is an ongoing action for the IDE Committee and People Team Diversity and Inclusion Officer (Steph Sloane) and Engagement Officer (Nicolette Robson are subscribed to many networks and online forums where they are the primary source of planning the participation and communicating to LMW | LMW IDE Committee have participated in the following relevant networks an forums. IDE Committee member Service Delivery and Operation Administration Officer (Teana Barton) expressed her interest attend the OzWater Conference 2023. As a member of the ED&I Committee, the conference covers a lot of ED&I topics which I would find beneficial to both my personal growth and to relay back to the ED&I committee. Teana was successful and attended the OzWater 2023. Teana Barton - Attending the conference will helped me to achieve my PDP goals and career growth within my position and member of the IDE Committee LMW's Diversity and Inclusion Officer is a member of the Diversity and Inclusion project team with IWN. This enables LMW to undertake trials with new technologies available to support employees wellbeing and reasonable adjustment IDE Committee members and staff of LMW attended some great online webinars throughout the year · Respect, Culture & diversity - Allyship Webinar · IWN Webinar Series - Empathy Lab · Local partnership 'Lunch and Learn' webinar to help prevent family violence #16DaysOfActivism · WaterAble's Celebration of International Day of People with a Disability - Hybrid Event | 2022 2023 2024 2025 | EDI Committee People Team
P4 - Community Engagement Strategy: Advance gender and intersectional equality as a shared responsibility across the broader community Participate in local diversity-focused events | Ongoing | Cultural awareness helps promote inclusivity, respect and understanding within our communities, workplaces, and organisations. LMW continuing involvement will advance education and inclusivity, and leading by example in the workplace. Participation in relevant networks and forums are an ongoing action for the IDE Committee and People Team. | Workshop at Lower Murray Water - GE Commissioner LMW participated in a workshop with Dr Niki Vincent (Gender Equality Commissioner) The People Team and People Leaders of LMW attended to learn all things Gender Equality and Dr Niki future vision regarding GE SuniTAFE NAIDOC Celebration 2023 Engagement Officer (Nicolette Robson) and Diversity and Inclusion Officer (Steph Sloane) were invited to the Dulka Yuppata Indigenous Training Centre to celebrate NAIDOC with the students, teachers and community. The Dulka Yuppata Indigenous Training Centre Is located on the Mildura Campus, Dulka Yuppata means ('Place of Learning') the First Nation Cultural Centre provides support and assistance to all First Nation learners that are enrolled at SuniTAFE, Mildura campus. Combined Mildura Gender Equality event with Dr Niki Vincent (Gender Equality Commissioner) LMW were grateful to attend another great workshop with Dr Niki Vincent. Commissioner Dr Niki Vincent spoke at the forum on her leadership journey, reflecting on her own personal experiences of Gender Discrimination and highlighting the importance of Gender Equality. She also discussed the importance of conducting gender impact assessments as a critical tool to combat Gender Biases in the development of policies, programs and services. Representatives from organisations in the Mildura region also spoke about their experience implementing the requirements of the Gender Equality Act (2020), reflecting on key achievements and challenges. LMW General Manager People Stakeholder (Deb Fankhauser) presented Commissioner Vincent also met with community and grassroots organisations in the region to better understand the structural and local challenges compounding Gender Inequality in Mildura. Attendees: GM People and Stakeholder (Deb Fankhauser), SM Talent and People Experience (Narelle South), Diversity & Inclusion Officer (Steph Sloane), HR Generalist (Toni Doxey), SM Customer Operations (Kaleb Sexton), Manager Organisational Performance (Nardia Sheriff), Engagement Officer (Nicolette Robson), Customer & Stakeholder Liaison (David Zacher) Mildura Rural City Council Walk against Family Violence for White Ribbon Day Friday 17 November 2023 - Langtree Mall to Power House Attendees: Steph Sloane, Nicolette Robson, Deb Fankhauser, Owen Russell, Rachele McHugh, Caz White and Sharyon Peart (Chair) | 2022 2023 2024 2025 | EDI Committee People Team
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Lower Murray Water's (LMWs) Gender Equality Framework and Action Plan (GEFAP - used interchangeably with GEAP) is supported internally and enabled through the People Team. LMW is engaged with many employee networks internally and externally and will continue to utilise these networks for support, including the VicWater Diversity and Inclusion Steering Committee, VicWater, HR Special Interest Group, Gender Equity Action Sunraysia, and Regional Gender Equality Community of Practice. The LMW Executive Team and LMW Board are committed to supporting and resourcing the GEFAP along with all actions contained within it, and will continue to be actively involved in monitoring and reporting. LMW continues to focus on human-centred consultation and engagement with current stakeholders, the ED&I Committee and the People Team manage the progress and maintain the momentum created during the creation and early implementation of the GEFAP. LMW's People Strategy confirms the responsibilities from managers throughout the business in the assessment of GIAs, equity in recruitment as well as ongoing employee retention and wellbeing strategies. LMW Board's Risk Appetite Statement confirms LMW has a low appetite for not taking risks to increase the diversity of our workforce. We continue to focus on recruitment of new staff as being key to ensuring our workforce represents the communities we serve. LMW has embraced and endorses a sector (water industry) approach; our General Manager People & Stakeholders is the chair of the Diversity & Inclusion Steering Committee for the Victorian Water Sector This committee consists of representatives from each Water Corporation across Victoria who work jointly on strategies and initiatives to support increased diversity, inclusion and equity across the sector. LMW's People Team administratively maintain the GEFAP and are responsible for collecting and maintaining the relevant data. Our Diversity & Inclusion Officer is employed full-time and her role is 100% related to GEFAP. Our HR Officer (full-time role) and HR Generalist (job shared role providing opportunity for a mother with young children to work part-time and providing an opportunity for personal development of another staff member from another team to utilise their theoretical skills gained in HR qualifications one day a week) are integral to the GEFAP success and approximately 40% of their roles impact on/are impacted by GEFAP. The same could be said for our People & Safety officer (full time) and Recruitment Coordinator (casual semi-retired individual with a wealth of skills gained across multiple industries who is able to support LMW processes and mentor/guide colleagues), The Senior Manager Talent & People Experience has dedicated approximately 80% of her time in the past quarter to GEFAP. LMW's General Manager People & Stakeholders (GMPS) (full-time) remains instrumental in the success of LMWs GEFAP and People Strategy. During the reporting period LMW experienced lengthy periods of vacancies in key senior management positions (Managing Director and General Managers), with the GMPS being the sole consistent incumbent between the two reporting periods. LMW's Engagement Officer continues to support the GEFAP through their communications and engagement activities. The real short-term to medium-term financial costs to the organisation in working towards its aim of true inclusion, diversity and equity is becoming increasingly apparent; and LMW must factor this into future budgets (noting as a water corporation we must submit 5 year water plans to Essential Services Commission (ESC) which determines budgets, so progress will be slower than preferred). Example of costs incurred in supporting an individual with caring commitments in moving to flexible hours (no loss in pay to them) meant a $13,000 contractor fee for 3.5 weeks work to bolster the early and late portions of the day where the individual could not be on-site to meet with construction crews. Job share arrangements are also being embraced, however we have not factored in the duplicate training costs, and the changing nature of superannuation payment arrangements, payroll tax, workers compensation premiums, handover opportunities as well as the impact on the remaining team members.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Lower Murray Water's (LMW's) overall workforce gender composition remains unchanged at 30% women (between 2021 and 2023). Workforce composition (% women) based on position level from MD - 2021 vs 2023: Positions once removed from MD level: Full-time contract (fixed term) - 50% vs 100% Positions twice removed from MD Level: Full-time permanent/on going - 57% vs 33% Full-time contract (fixed term) - 17% vs 23% Part-time permanent/ongoing - 100% (unchanged) Positions three times removed from MD level: Full-time permanent/on going - 58% vs 54% Full-time contract (fixed term) - 21% vs 10% Part-time permanent/ongoing - 100% (unchanged) Part-time contract (fixed term) - N/A vs 100% Casual - N/A vs 0% Positions four times removed from MD level: Full-time permanent/ongoing - 36% vs 35% Full-time contract (fixed term) - 67% vs 80% Part-time permanent/ongoing - 89% vs 80% Part-time contract (fixed term) - N/A vs 100% Casual - N/A vs 0% Positions five times removed from MD level: Full-time permanent/ongoing - 2% (unchanged) Full-time contract (fixed term) - 33% vs 20% Part-time permanent/ongoing - N/A vs 0% Positions six times removed from MD level: Full-time permanent/ongoing - 5% vs 9% Part-time permanent/ongoing - N/A vs 0% Positions seven times removed from MD level: Full-time permanent/ongoing - N/A vs 0% The composition by employment basis has shown an increase in the number of part-time opportunities between reporting periods; this has been embraced by men as well as women. Previously 94% of the roles were full-time with only 6% being part-time. Now 88% are full-time, 10% are part-time and 2% are casual. Interestingly, men make up 100% of our casual workforce in 2023. LMW has recognised and embraced job-share arrangements and continues to consciously challenge the assumption of full-time position defaults. While we have seen a very slight reduction in percentage of women represented in the full-time split (26% in 2021, compared with 25% in 2023), the number of men who have taken on part-time opportunities has significantly grown (this is further highlighted in the flexible work arrangement section below). These results demonstrate a positive shift in the composition of LMW’s workforce enabling both men and women to negotiate part time arrangements to better balance work and family commitments. Women made up 30% of new recruits in the 2021 reporting period and this has risen to 38% in 2023. We have used the anonymity of the People Matter Survey (PMS) results of 2021 and 2023 to confirm our employee data set to confirm that no individual currently identifies as gender diverse, We recognise this is not consistent with general community, and are working on creating a safer, fail-safe environment so as employees can confidently disclose what we believe to be a more diverse workforce that what is currently being disclosed. |  | Yes |  | Yes |  | Yes | Yes | As detailed in the Strategies and Measures and Resourcing your GEAP tabs
Gender composition of governing bodies | Yes | In our 2021 audit women represented 50% of LMW governing body in the year to 30 June 2021. In our 2023 progress audit this remained the same. Our Chairperson of the board in 2023 is the same woman who held the position in 2021. As a water corporation, LMW governing bodies are appointed to their position for 4 years by the Victorian Minister for Water. LMW's ability to influence the composition of the board is therefore limited. |  | Yes | [5 empty] | As detailed in the Strategies and Measures tab
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | During the preparation of our progress report, we have identified an error in our Gender pay data that was submitted to the Commission in 2021. The reporting requirements specify the inclusion of all monies paid to each employee including allowances and overtime. We have confirmed that LMW submitted data in 2021 which excluded allowances and overtime. Current business systems make it very difficult to retrieve this data accurately and this has required us to extract allowance and overtime data separately and then add it to annual salaries of each employee. We are unable to include meal and travel allowances as they are not paid through our payroll system. We will work on this as a continuous improvement for future reporting periods and have flagged the requirement for the Business Transformation Program (BTP) to consider and incorporate improvements that support better reporting in this regard. We have received confirmation from the Commission that we can resubmit our 2021, however it cannot be done prior to finalising our 2023 progress report. The Commission have provided a workaround enabling LMW to process our 2021 audit locally so we can determine the updated results of the 2021 audit for the purpose of progress report preparation. We have used the 2021 workplace gender audit template to make changes to our 2021 data and locally calculate the corrected Gender Pay Gap data to be: 6.4% for mean total remuneration pay gap (previously reported and published as 4.2%) - i.e. for every $100 paid to a paid, $93.60 was paid to a woman -0.3 for median total remuneration pay gap (previously reported and published as -4.2%) 3.6% for mean annualised base salary pay gap (i.e. remains the same as previously reported and published) -4.2% for median annualised base salary (i.e. remains the same as previously reported and published) The 2023 mean total remuneration pay gap for women is 6.2% (i.e. for every $100 paid to a man, $93.80 was paid to a woman). This suggests that LMW has remained consistent in overall gender pay gap from 2021 to 2023, which we feel belies the effort that has been put into enhancing diversity and inclusion and our efforts to address ongoing inequality. . As LMW are required to submit progress audit reports every two years, its timely to note the following: - Both the 2021 and 2023 dataset included VMFRP (separately funded, but auspiced via LMW and the staff are considered LMW employees) project staff. - The VMFRP project workforce bolster the overall average base salary and total remuneration figures in 2021 and 2023 as the base salaries are significantly higher than non-VMFRP employees. - The gender composition of the VMFRP team in 2021 and 2023 was 33% women and 22% men respectively. As at the time of this report, the reduced VMFRP project workforce (3 contract staff) comprises 66% women. It is expected that by the 2025 progress report VMFRP salaries will no longer form part of LMW’s dataset. This means the comparative buoying of women’s salaries that applies in the 2021 and 2023 dataset will no longer exist. (The average total remuneration for VMFRP project staff was $288,674 as at 30 June 2021, and $325,608 as at 30 June 2023. In comparison, the non-VMFRP staff average total remuneration was $100,051 and $103,449 respectively). While we expect inroads to be made toward closing the gender pay gap in real terms for employees by 2025, the expected cessation of VMFRP salaries will impact the level of improvement achieved. There is a risk that our Gender pay gap will increase when the VMFRP position concludes if we do not make significant progress across our baseline workforce in the next 18 months before the 2025 progress report. Post submission of the current progress report, the People team will prepare a gender pay gap assessment excluding the VMFRP positions so we can understand the direct impact these positions have on our overall result to ensure our plan actions and activities will effectively manage this risk as much as possible. |  | Yes |  | Yes | Yes |  | Yes | As detailed in the Strategies and Measures and Resourcing your GEAP tabs
Sexual harassment in the workplace | Yes | Our 2021 People Matter Survey (PMS) data showed that 2% of women and 2% of men who responded to the survey had experienced sexual harassment in the workplace. In 2023, our PMS data showed that 2% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace. There were nil formal reports of sexual harassment in 2023. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. Commencement of LMWs newly created role of Senior Manager Health and Safety has seen demonstrable improvement of our Safety culture and enhancing our OHS Management System in the second half of 2023 calendar year. After analysing the then-current safety system (Rapid Global), it was identified the safety reporting mechanism in place at LMW was unrestricted internally, and the process of identifying a secure, integratable safety incident management system commenced. Senior Manager Health and Safety presented a business case to implement Beakon to be LMW new safety system, and at the time of this report, the system has been implemented. Work is currently underway in testing the security of sensitive information, as is the work in educating our employees of the need to readily report hazards (including those of a sexual or sex-based nature).. We are aiming to achieve this in early 2024. In the meantime we will progress on educating our staff and providing assistance to seek support and reporting sexual harassment in our workplace. Lower Murray Water is committed to providing safe, inclusive and respectful workplaces, which are free from sexual harassment. We have defined policies and procedures regarding the reporting and investigation processes, training for all staff on what constitutes bullying and harassment (including sexual harassment) and discrimination, and LMW’s zero tolerance approach to any such behaviour. We forecast a rise in the reporting of associated hazards, but a reduction in actual instances of harassment as awareness and confidence grows.
Recruitment and promotion practices in the workplace | Yes | Recruitment In 2021 women only represented 30% of LMW's new recruits (in the year to 30 June 2021). In our 2023 progress audit, this increased 8% to 38% In 2023, of the women recruitment, 50% were recruited into full-time ongoing positions, 22% info full-time limited tenure positions, 17% into part-time ongoing and 11% into part-time limited tenure positions. There were no casual positions awarded to women during the 2023 audit period. Nil staff identified as non-binary or gender diverse in 2021, and again in 2023 (internal reporting). As previously discussed (in Strategies and measures tab), we are actively working with our IT team to devise ways in which we can collect and securely store sensitive information, then we can continue to encourage staff to disclose in confidence, their true authentic identities. Promotions Our 2021 audit data showed that 56% of promotions were awarded to women, and this dropped in 2023 to 32%. We have refined the limited systems we have available to collect and monitor required recruitment and progression data since 2021 to ensure results are more authentic to the intent. Entry (recruitment) and Exit figures reported in 2021 (30% and 35% respectively), demonstrate comparable results and illustrate a deliberate focus on women and diversity in the workplace (women now represent 38% of new hires) through our recruitment process. Now that the collection and reporting of data forms part of the legislative regulation, the People team are actively working with the BTP team and IT department to enhance accuracy of data currently sourced from a variety of independent systems (payroll figures, manual spreadsheets maintained versus TechOne systems) Until 2022, LMW historically maintained executive level staff for many years, with very few exits. Of the five executive positions in place in 2021 and 2023, only one of the incumbents was represented in both 2021 and 2023 audit datasets. Unfortunately, the high turnover wasn't just restricted to the executive; it was consistent across the organisation and at the end of the 2023 reporting period, we had reached a staff turnover rate of just over 24%. Having made it through these turbulent times, our organisation now stands in very good stead, commencing the new calendar year with an Executive team balanced at 50% women, and a strong commitment from the team to address inequities and disadvantage moving forward.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | The number of formal flexible work arrangements (FWAs) have risen significantly, from just 6% of the workforce in 2021, to one in four employees having a formal FWA in place in 2023. Of the one in four employees who have a formal FWA in place, 38% are men which is more than double the 2021 figure of 17%. As highlighted previously; improvements in equality, diversity, and inclusion benefit everyone, including men. The gender composition of parental leave takers has slightly altered from 33% Women in 2021 to 36% Women in 2023. These figures are consistent with our workforce composition given 30% of our overall workforce are women. The positive message in this regard is the level of engagement in our men accessing parental leave to active roles in family life. Of significance, and reflective of enhanced Enterprise Agreement provisions coming into effect at the start of 2022, the average weeks of parental leave taken has risen from 2.5 weeks for women in 2021 to 22.5 weeks in 2023, and men have increased their average parental leave taken from 2 weeks in 2021 to 3.9 weeks in 2023. We recognise the increased confidence in staff seeking support from the organisation when facing domestic and family violence. These cultural shifts are testament to our progress which will transfer through to other aspects of inclusion and equality in the coming years. Carers leave data: In 2021: 29 women and 50 men accessed carers leave. In 2023: 36 women and 63 men accessed carers leave.
Gendered segregation within the workplace | Yes | Notwithstanding the changes in the ANZSCO workforce coding between 2021 and 2023, we are seeing a trend towards a more even distribution of women across occupational categories – acknowledging there is still significant opportunities for improvement here. Women now represent a greater portion of the ‘traditional male dominated’ roles such as Managers, and we have more Men represented in clerical and sales (revenue services) roles which have historically been predominately filled by women.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled